## ANNEX A - ICC Guidelines (hidden)
Operations and Maintenance of Bicol International Airport
List of documentary requirements for unsolicited projects pursuant to Section 10.7 of the 2022 BOT Law IRR
No. | Document (should be in searchable format) | Description/Remarks | Agency Remarks (indicate which specific tab/cells/ annex/page(s) the document or information is found) | Evaluator Remarks | Project Name (as stated in document)
1 | Letter of the Agency to the ICC submitting the project for approval | The letter should indicate the following: | Submitted: DOTr_DRP_20230510_1_ DOTr and CAAP Re-endorsement | Document submitted Submitted as "re-endorsement" and as per ICC Guidelines, this should be considered as new project | Operations and Maintenance of Bicol International Airport | "Re-endorsement" letter does not include a description and expected output and outcome, but instead refers to a previous endorsement letter.
|  | a. project name |  | Information provided
|  | b. description |  | Information provided in the annexed letter dated March 22, 2023
|  | c. expected output and outcome |  | Information provided in the annexed letter dated March 22, 2023
|  | d. implementation period |  | Information provided in the annexed letter dated March 22, 2023
|  | e. list of all documents being submitted in support of the project proposal |  | Information provided
|  | f. the full and unqualified endorsement of the Head of the Agency submitting the project for ICC/NEDA Board approval |  | Information provided
2 | Company profile of the project proponent | Pursuant to Sections 10.7, 10.6(c), 10.4(a)(i), a company profile showing the company’s mission, business lines, past and ongoing projects, and, financial highlights shall be submitted. | Submitted: DOTr_DRP_20230510_2_Business Plan DOTr_DRP_20230510_2_Company profile | Document submitted
3 | Complete Feasibility Study (F/S) | Pursuant to Sections 2.7 and 10.4(a)(ii) of the Revised 2022 BOT Law IRR, a complete feasibility study (F/S) should contain information that are up-to-date and are not older than three (3) years as of the date of submission to the Approving Body. The F/S should also contain the following information: | Submitted: DOTr_DRP_20230510_3_Complete Feasibility Study (F-S)_clean DOTr_DRP_20230510_3_Complete Feasibility Study (F-S)_marked | Document submitted | Operations and Maintenance of Bicol International Airport
|  | a. problem definition or statement of objectives | Section 1 | Information provided
|  | b. project description* | Section 1 | Information provided |  |  | This section presents the project’s configuration and scope of works particularly a brief description of the components, the location and the areas of service/influence. This should clearly indicate the outputs (e.g., products, services, target users) of the project.
|  | c. project context in the Agency’s overall strategy/program* | Section 2.6 Project Linkages | Information provided is incomplete No mention of timelines and investment requirement as required in the annexed detailed description of requirements |  | FS mentions the National Transport Policy. No mention of overall development timelines, and investment requirements. | This pertains to the overview of the concerned Department’s national strategy and program, including overall development outcomes, timelines, and investment requirements, and the specific link of the proposed project outputs, timelines and investment requirements to achieve the Department’s national strategy and program.
|  | d. sectoral program context* | Section 2.1, 2.2 | Information provided |  | no linkage with other initiatives in the sector. Section 4.13 of APER discloses the AIC is also the OP for Bohol and Laguindingan. | This section provides a brief overview of sector targets, existing programs and sectoral gaps based on existing master plans/sectoral programs, how the proposed project addresses the needs, priorities and objectives of the sector, and linkage of the proposal with other initiatives in the sector as well as related projects in other sectors.
|  | e. regional and spatial context* | Section 2.1, 2.2 | Information provided |  | provide easy access to the region and connect it to the global market, identifies connectivity as a core strategy | This section indicates the geographical coverage of the proposed project and its linkage with other projects within the region and across the country. For area specific projects, justification for the choice of area/s should be clearly stated. This may include, as annexes, location map and other relevant technical diagrams.
|  | f. expected outcomes and key success indicators, including means of verification and key assumptions | As discussed with TWG, proponent has updated FS and CA to refer to 12th edition. Proponent working with Technical Consultant to do analysis on comparison of 10th and 12th, to check and review possible required updates to the MPSS. | Information provided
|  | g. analysis of technical solutions or alternatives, including analysis of risks and impacts* | Section 3.2 | Information provided
|  | h. stakeholder analysis* | Section 2.10 | Information provided |  | identifies stakeholders. only covers consultations with the Grantor. No "public consultation" done. | The stakeholder analysis should include a discussion on the results of the conducted public consultations, including how concerns are mitigated.
|  | i. project costs* | Section 2.4, 4.2 | Information provided |  | does not specify "cost of chosen technology and mitigating related risks and impacts" | For operations and maintenance PPP projects, the Project Cost refers to the present value of the costs incurred in delivering the contracted service, including any reinvestment requirements as provided in the approved contract. Project cost should also include cost of a chosen technology and mitigating related risks and impacts.
|  | j. legal due diligence, which includes policy and regulatory framework of the market/s affected by the project, and institutional analysis | Section 2.3 | Information provided
|  | k. demand analysis* | Section 3.1 | Information provided |  |  | An analysis of the market as well as the existing and projected demand for the project. This includes assumptions in the demand forecast, the historical data used as basis in the forecast, if any, and an assessment on the appropriateness of project interventions, considering market characteristics (e.g., user fees vs willingness-to-pay).
|  | l. information on the proposed tariff structure | Section 4.5 | Information provided
|  | m. financial analysis (including information on project revenues consistent with the financial model)* | Section 4.6 | Information provided
|  | n. economic analysis (including information on economic benefits and cost consistent with the economic model)* | Section 5 | Information provided
|  | o. project safeguards*  environmental quality  natural and cultural resources sustainability  climate change and hazards  equity in development benefits  health and safety | Section 8 | Information provided
|  | p. risk allocation and risk mitigating plan | Section 7.4 | Information provided
|  | q. value for money analysis* | Section 6.1 | Information provided
|  | r. public-private Partnership (PPP) contractual arrangement options and assessment of the proposed contractual arrangement | Section 1 and 2.3 | Information provided
|  | s. information on job creation (from development to operation and maintenance)/employment impact of the project, and number and types of jobs with corresponding sex-aggregated data and amount of wages/salaries | Section 5.6 | Information provided
4 | Electronic copy of the economic model | Pursuant to Sections 2.7 and 1.3(j) of the Revised 2022 BOT Law IRR, the economic model should: a. be in traceable formula format (assumptions/inputs shall be shown in a summary sheet that are linked to the relevant work sheets of the model) b. contain information that are up-to-date and are not older than three (3) years as of the date of submission to the approving body | Submitted: DOTr_DRP_20230510_4 and 5_Electronic copy of the financial and economic model | Document submitted inputs sheet contains hard coded values for traffic, tariff, revenue sharing, among others. | Bicol International Airport
|  | The economic model should also contain the following: a. economic benefits and costs of a project b. assumptions used in calculating economic benefits, and conversion of financial costs to economic costs c. calculation of economic viability (i.e., economic internal rate of return; economic net present value; benefits-cost ratio) |  | Formula errors |  | error in sensitivity analysis
Moreover, the submission shall consider the current situation, as may be applicable (e.g., impacts of a pandemic on demand and costs)
5 | Electronic copy of the financial model | Pursuant to Sections 2.7, 1.3(l), 2.10(i), 15.2(a)(ii), and 15.2(b) of the Revised 2022 BOT Law IRR, the financial model should: a. be in traceable formula format (assumptions/inputs shall be shown in a summary sheet that are linked to the relevant work sheets of the model) b. contain information that are up-to-date and are not older than three (3) years as of the date of submission to the approving body | Submitted: DOTr_DRP_20230510_4 and 5_Electronic copy of the financial and economic model | Document submitted inputs sheet contains hard coded values for traffic, tariff, revenue sharing, among others.
|  | The financial model should also contain the following: a. projected balance sheet of the project for its full life cycle b. assumptions used in calculating the financial revenues and financial costs c. income statement of the project for its full life cycle d. cash flows statement of a project for its full life cycle e. calculations on financial viability (i.e., free cash flows to firm and equity holders; project and equity internal rates of return; project and equity net present value; weighted average cost of capital; cost of equity components based on Capital Asset Pricing Model (CAPM) f. calculations on bankability (i.e., debt service coverage ratio) g. amounts to be paid and schedule of payments of firm liabilities h. VFM/Public Sector Comparator model |  | Information provided is incomplete cost of equity components based on CAPM calculation and DSCR not provided, but can be derived based on the provided information
Moreover, the submission shall consider the current situation, as may be applicable (e.g., impacts of a pandemic on demand and costs)
6 | Proposed project Parameters Terms and Conditions (PTC) | Pursuant to Section 2.8 of the Revised 2022 BOT Law IRR, the Agency should submit a proposed set of PTCs for the project. The Agency shall submit its Proposed Parameters Terms and Conditions (PTCs) using the following forms: | Submitted: DOTr_DRP_20230510_6_Proposed project PTC |  | Operations and Maintenance of Bicol International Airport
|  | PTC Form 1 (General Parameters, Terms, and Conditions) which includes the general information about the proposed project as outlined in Section 2.8 of the Revised 2022 BOT Law IRR. | Submitted: DOTr_DRP_20230510_6_Proposed project PTC | Document submitted |  | references Draft CA 2.1 states O&M contractual arrangement, APER states OAT contractual arrangement
|  | PTC Form 2 (Actual and potential conflict between the proposed project and other government projects) which includes the Agency’s assessment of the actual and potential conflicts between the proposed project and other government projects. | Submitted: DOTr_DRP_20230510_6_PTC Form 3 | Document submitted
|  | PTC Form 3 (Firm Liabilities*) which includes the following details regarding the proposed government liabilities for the proposed project: a. Proposed government undertakings (GUs) identified in Section 13.3 of the Revised 2022 BOT Law IRR, as may be applicable. Such GUs may include Viability Gap Funding as defined in Section 1.3(ll) and indicated in Section 15.1 of the BOT Law IRR. For proposed GUs that come in the form of Direct Government Subsidy, the valuations of government assets or property as determined by a government financial institution (GFI) or an independent property appraiser (IPA) should be included. b. Government repayments pursuant to Section 12.16 of the Revised 2022 BOT Law IRR | Submitted: DOTr_DRP_20230510_6_PTC Form 3 DOTr defers to the review and observations of the TWG, NEDA-ICC, and OSG on the final CAs. | Document submitted
|  | PTC Form 4 (Proposed Risk Allocation and Contingent Liabilities* of the government) which includes the risk allocation matrix, the possible resulting contingent liabilities for risks taken on by the government, and the proposed risk mitigating measures. PTC Form 4 effectively serves as the risk mitigation plan required under Section 2.8 of the Revised 2022 BOT Law IRR. Section 15.3(b) of the Revised 2022 BOT Law IRR details the following requirements to be included in the plan: a. a list of all risks assumed by the government under the contract b. risks assumed by the Agency c. risk mitigating measures d. estimated costs to be incurred e. target dates to have each measure in place f. appropriate action plan by the Agency to manage each type of risk The contents of the submitted proposed PTCs should be consistent with the contents of the submitted financial and economic models. (See PTC Forms 1-4) | Submitted: DOTr_DRP_20230510_6_Proposed project Parameters Terms and Conditions (PTC) | Document submitted
7 | Agency Project Evaluation Report (APER) | The Agency PER is a summary of the Agency’s due diligence on the proposed PPP project, which should include the following sections: | Submitted: DOTr_DRP_20230510_7_APER | Document submitted | Operations and Maintenance of Bicol International Airport
|  | a. Assessment on the completeness of submission pursuant to Sec 2.7 and 10.4 of the IRR and this ICC Guidelines | Section 3.1 Completeness of Submission | Information provided |  | Pursuant to 10.4.a.iii of the Revised 2022 IRR, lacks an assessment on the consistency of draft contract with Section 4.3 of the Revised 2022 IRR.
|  | b. Assessment of project eligibility with respect to Sections 2.3, 10.1, 10.2, and 10.3 | Section 3.2 Project Eligibility | Information provided is incomplete |  | The APER provides an assessment of project eligibility in terms of presence of a new technology; It does not provide an assessment of project eligibility in terms of: 1. Absence of direct government guarantee,direct government subsidy or direct government equity required 2. Not a component of an approved project
|  | c. Project context in the implementing agency’s overall strategy/program | Section 2.2.2 Project context in the implementing agency’s overall strategy/program | Information provided
|  | d. Assessment of the qualification of the proponent in terms of legal requirements, firm experience or track record, and financial capability | Section 3.3. Qualification of the Proponent | Information provided
|  | e. Assessment of the appropriateness of the chosen contractual arrangement | Section 3.4. Appropriateness of Contractual Arrangement | Information provided |  | For discussion *To consult principals if assessment is valid: "DOTr defers to the review and observations of the TWG, NEDA-ICC, and OSG on the final Concessionaire Agreement xxx"
|  | f. Agency’s findings on the following: i. Technical evaluation ii. Demand analysis iii. Environmental evaluation including climate change resiliency considerations iv. Institutional analysis v. Social analysis including gender safeguard vi. Economic analysis vii. Financial analysis | Section 4. Project Evaluation | Information provided
|  | For the findings on the Economic and Financial analysis, include analysis of robustness and reasonableness of assumptions used in the economic and financial models as discussed in ICC Evaluation Criteria for the Review of Public – Private Partnership Projects For unsolicited proposals whose subject matter is covered by existing comparable feasibility study/ies, the IA may include a comparative evaluation of the level of detail (LoD) between the unsolicited proposal FS and the relevant comparable FS. | No comparable unsolicited proposal and/or feasibility study
|  | g. Information on the proposed tariff structure | Section 5. Proposed Tariff Structure | Information provided
|  | h. Justification of the preferred bid parameter | Section 6. Preferred Bid Parameter | Information provided |  | bid parameter not specified in stated CA section
|  | i. Recommended reasonable rate of return (RROR) | Section 7. Recommended Reasonable Rate of Return (RROR) | Information provided
8 | Valuation report on the valuation of government assets | Pursuant to Sections 13.3(c) of the Revised 2022 BOT Law IRR, a report on the valuation of contributed government assets or property/ies that are to be used/included in the financial model. The valuation shall be as determined by a GFI or by an IPA included in the list of Accredited Asset Valuers of the Securities and Exchange Commission (SEC). The report should not be older than one (1) year from the date of submission to the Approving Body. In case of IPA, proof of the valuation company’s inclusion in the list of Accredited Asset Valuers of the SEC must be also submitted. | Submitted: DOTr_DRP_20230510_8_Valuation report on the valuation of government assets_CAAP DOTr_DRP_20230510_8_Valuation report on the valuation of government assets_DOTr endorsement to COA DOTr_DRP_20230510_8_Valuation report on the valuation of government assets_DOTr | Document submitted
9 | Gender responsiveness checklist | Pursuant to the ICC Memorandum titled “ICC Policy on Integrating the Harmonized Gender and Development Guidelines (HGDG) in the ICC Process” dated September 30, 2016, the Agencies are required to accomplish and submit Gender Responsiveness Checklist (the Combined Generic Checklist for the Project Identification and Design Stages). The guidelines for accomplishing the Gender-Responsiveness Checklist can be accessed at: https://neda.gov.ph/wp- content/uploads/2020/09/Guidelines-in-Accomplishing-the-ICC-PE-on- Gender-Responsiveness-Checklist.pdf | Submitted: DOTr_DRP_20230510_9_Gender responsiveness checklist | Document submitted | Unsolicited Proposal for the New Bicol International Airport
10 | Location map (with e- copy) | A diagram that outlines the project site should include major landmarks and infrastructure/ facilities within the project area. | Submitted: DOTr_DRP_20230510_10_Location map (with e- copy) | Document submitted
11 | Right of Way Acquisition (ROWA)* / Resettlement Action Plan (RAP) or a Certification from the Head of Agency that all project land and other ROW have been acquired (for projects requiring project land or ROW) | A document showing the extent of the project’s ROW requirements and estimated costs. At the minimum, the submitted plan(s) should include the following information: | Not applicable. The Project does not require additional land. | Not applicable
a. Project Affected Persons (PAPs): a) estimated number (PAPs, households); b) profile/group: IPs, owners, ISFs, etc.; c) compensation package, with estimated amount (per PAP or per household), including livelihood program/Social Development Program, if any;
b. Affected structures: a) estimated number; b) type: commercial, residential, government asset, etc. ; c) compensation package, with estimated amount (per affected structure);
c. Utilities (electricity, water, ICT/Telecoms, etc.): a) estimated number; b) type of utility; c) relocation cost, with amount (per affected utility), d. Institutional arrangement (parties involved and their responsibilities); e. Activities and implementation period; and f. Applicable laws, rules and regulations. ROWA and RAP costs must be specified and itemized in the financial model (if the project does not involve an acquisition of land for the project, indicate 0). The ROW and resettlement costs are typically significant expense items that the proponent of an unsolicited proposal must bear. This must be clearly reflected in the PTC and financial model.
12 | Certification from Head of Agency on the conduct of the mandated evaluation pursuant to Section 10.6 of the Revised 2022 BOT Law IRR | Certification from Head of Agency, and supporting documentation, that it has done the mandated evaluation of the unsolicited proposal, pursuant to Section 10.6(c)(i) of the Revised 2022 BOT Law IRR (See prescribed Certification template) | Submitted: DOTr_DRP_20230510_12_Certification from Head of Agency | Document submitted | Operations and Maintenance of Bicol International Airport
13 | Original proponent status (OPS) by the Agency | Copy of the document granting the OPS by the Agency to the private proponent | Submitted: DOTr_DRP_20230510_13_OPS DOTr_DRP_20230510_13_Signed Board Secretary's Certificate DOTr_DRP_20230510_17_Draft CAAP Board Resolution | Document submitted | Operation and Maintenance of the Bicol International Airport | CAAP - Board Resolution granting OPS unsigned, Secretary's Certificate signed
14 | Draft PPP contract | Pursuant to Sections 10.4(a)(iii) of the Revised 2022 BOT Law IRR, the draft contract to be submitted should contain the mandatory terms and conditions set forth in Section 4.3 of the Revised 2022 BOT Law IRR. | Submitted: DOTr_DRP_20230510_14_Draft PPP contract_cover DOTr_DRP_20230510_14_Draft PPP contract DOTr_DRP_20230510_14_Draft PPP contract_annexes DOTr defers to the review and observations of the TWG, NEDA-ICC, and OSG on the final CAs. The draft PPP Contract reflects DOTr as the sole grantor for the Project. However, DOTr and CAAP commit to submitting a revised version of the draft PPP Contract, reflecting DOTr and CAAP as co-grantors, during the evaluation period of the ICC. | Document submitted (Draft contract states only DOTr as grantor and no mention of the CAAP as co-grantor) | Bicol International Airport
15 | Unsolicited Proposal Assessment Forms (USP AFs) | The agency shall fill out the following forms to establish the project proponent’s legal eligibility pursuant to Section 5.4(a), firm experience or track record pursuant to Section 5.4(b), and financial capability pursuant to Section 5.4(c) of the Revised 2022 BOT Law IRR. | Submitted: DOTr_DRP_20230510_15_USP AF5_Unsolicited Proposal Assessment Forms (USP AFs) |  | Operations and Maintenance of Bicol International Airport
| a. USP AF 1: Assessment of the project proponent’s legal eligibility, including proof of legal eligibility | The following proofs of legal eligibility must be submitted by the proponent:  If the proponent is composed of an individual or a group of individuals (including partnerships), but not a corporation, proof of identity of each individual  If the proponent is a corporation - Copy of SEC Registration (Sec. 5.4(a)(i) of the BOT Law IRR) - Copy of completely filled general information sheet (GIS) with proof of receipt by SEC - Sworn certification by the corporate secretary to the authenticity of submitted documents  If the proponent is a consortium - An agreement among members to form a consortium to undertake the project - An undertaking, binding the consortium members to be jointly and severally liable for the obligations of the project proponent under the contract (Sec. 5.4(a)(iv) of the BOT Law IRR) - Shareholder agreement based on proposed ownership structure (Sec. 5.4(c)(i)(1) of the BOT Law IRR)  If the proponent is a cooperative - Copy of CDA Registration (Sec. 5.4(a)(i) (ii) and (iii) of the BOT Law IRR) If the proponent and the operator are two separate independent entities, the nominated operator must submit the following:  If the operator is composed of an individual or a group of individuals (including partnerships), but not a corporation, proof of identity of each individual  If the operator is a corporation - Copy of SEC registration (Sec. 5.4(a)(ii) of the BOT Law IRR) - Copy of completely filled SEC GIS with proof of receipt by SEC - Sworn certification by the corporate secretary to the authenticity of submitted documents  If the operator is a cooperative - Copy of CDA Registration (Sec. 5.4(a)(i) (ii) and (iii) of the BOT Law IRR) For each contractor participating in construction PCAB license if a Filipino company, or its equivalent issued by the country of origin, if a foreign company (Sec. 5.4 (a)(v) of the BOT Law IRR) For projects involving the operations of public utilities, the Filipino citizenship for individuals, and the 60% Filipino ownership or interest, for corporations and consortiums respectively, are required. | Submitted: DOTr_DRP_20230510_15_USP AF1 | Document submitted
| b. USP AF 2: Assessment of the project proponent’s experience or track record, including proof of experience or track record | The proponent by itself or through the member-firms in case of a consortium, or through its Contractor and/or nominated entities must submit the following:  A list of projects similar or related to the proposed project, including information on the asset owner of the project, the location of the project, and the year the project was undertaken. A certification from the asset owner that the entity had successfully undertaken the project or the activity under the project in the list must be submitted.  A list of key personnel and for each personnel, the role in the project, a description of relevant experience and the years of experience in the role provided. A curriculum vitae showing the year, duration, location and nature of experiences relevant to the project should be attached for each personnel.  If the nominated entities are bound by a technical services agreement (TSA), the following must be submitted: o proof that the nominated entities are bound by a TSA o a list of projects similar or related to the project/s to be bid undertaken by the nominated entities that will provide the technical services  If undecided on a specific Contractor and/or nominated entities, the proponent must submit the following: o a short list of Contractors and/or nominated entities from among which it will select from o statements from the short-listed Contractors and/or nominated entities indicating willingness to participate in the project and capacity to undertake the requirements of the proposed project If the proponent is a consortium, the following must also be submitted:  A business plan, containing the following information: o Members of the consortium o Equity interest/contribution of each member to the consortium, their prospective Contractor(s) and/or nominated entities, if the experience of their Contractor(s) and/or nominated entities are necessary for the determination of the capacity of the consortium to undertake the project o Description of the respective roles of the members and Contractors and/or nominated entities in the project, including the prospective facility operator(s), if applicable. | Submitted: DOTr_DRP_20230510_15_USP AF2 | Information provided Information provided for list of personel; Information incomplete for CV |  | a. ok for Aboitiz Construction. Certification for daa issued by daa. b. ok c. willingness to participate - "if awarded, shall formally enter into a contract" |  | - Safety supervisor lacks CV of Noel Tanillon (Name in the CV provided for safety supervisor is different form list of personel)
| c. USP AF 3: Assessment of the project proponent’s financial capability, including proof of financial capability | The following proofs of financial capability must be submitted by the proponent:  Latest audited financial statement of each consortium member from previous reporting period of the period of evaluation (Sec. 5.4 (c)(i)(1) of the BOT Law IRR) For equity  If equity shall be financed through set-aside deposit, proof of set- aside deposit equivalent to the equity requirement of the project from a domestic universal/commercial bank or an international bank that is authorized by the BSP to transact in the Philippines. The document must indicate that the set-aside deposit is committed solely for the project For debt  Letter testimonial from each bank that will provide the debt requirement for the project attesting that :1) the prospective Project Proponent and/or members of the consortium are banking with them; 2) the Project Proponent and/or members of the consortium are in good financial standing and/or are qualified to obtain credit accommodations from such banks, or a statement of similar tenor, to finance the project equivalent to the value of the debt requirement in the proposal. The testimonial must come from a domestic universal/commercial bank or an international bank that is authorized by the BSP to transact in the Philippines. (Sec. 5.4 (c)(ii) of the BOT Law IRR) | Submitted: DOTr_DRP_20230510_15_USP AF2 | Document submitted *(AFS submitted is as of 2021)
| d. USP AF 4: Assessment of the draft contract | This form shall establish the consistency of the draft contract pursuant to Section 4.3 of the Revised 2022 BOT Law IRR. | Submitted: DOTr_DRP_20230510_15_Unsolicited Proposal Assessment Forms (USP AFs) | Document submitted
| For projects with proposed new technology/concept: e. USP AF 5: Assessment of proposed new technology/ concept | The agency shall establish the eligibility of the project pursuant to Section 10.1(a) and 10.2 of the Revised 2022 BOT Law IRR. (See USP Assessment Forms 1-5) | Submitted: DOTr_DRP_20230510_15_USP AF5 | Document submitted
Additional requirement for agencies submitting as an attached agency: a. The full and unqualified endorsement by the Head of Mother Agency should be attached to the cover letter; |  |  | Submitted: DOTr_DRP_20230510_1_ DOTr and CAAP Re-endorsement
Additional requirements for projects with proposed new technology/concept: a. The USP AF 5 (assessment of proposed new technology/concept) should be filled out by the agency b. The following must be submitted: i. Certification from the implementing agency that based on its assessment, the new concept or technology possesses any of the features specified in Section 10.2 of the Revised 2022 BOT Law IRR and other features that would have a positive impact on the implementation and operations of the project. Such certification may also be sought from relevant government agencies/bodies/ institutions/etc., with knowledge of the proposed new concept or technology ii. Details of the new concept or technology and cost-benefit analysis comparing the new concept/ technology with traditional ones iii. Proof that the proponent itself has, through or any of its consortium members or contractors or nominated entities have, directly and successfully implemented the new concept or technology at a scale similar to the proposed project. The information disclosed must be in sufficient detail so as to allow the proper evaluation of the new concept or technology. |  |  | Submitted: DOTr_DRP_20230510_15_USP AF5 | Document submitted | Upgrade, Expansion, Operation and Maintenance of the Bicol International Airport | Listed "Bicol (New Legaspi) International Airport" is construction of airport.
Additional requirements for projects undertaken by Government-Owned and Controlled Corporations: a. Electronic copy of the financial model of the GOCC’s projected cash flows, income statement, and balance sheet without the project, for the duration or life of the project. This should be in traceable format, including relevant assumptions. b. Copy of the Board Resolution, duly signed by the members, approving the proposed project. |  |  | a. DOTr_DRP_20230510_16_Electronic copy of the financial model of CAAP_WITHOUT DRP TAG CGY DOTr_DRP_20230510_16_Electronic copy of the financial model of CAAP_WITH DRP TAG CGY b. DOTr_DRP_20230510_17_Signed Board Secretary's Certificate DOTr_DRP_20230510_17_Draft CAAP Board Resolution | a. Document submitted b. Document not submitted | Operation and Management of the Bicol International Airport | financial model without the project: 1. Income Statement row 140 - hardcoded amounts 2. interest income 35 yrs row 9, 23 - hardcoded amounts - exchange rate (Sheet 2, C7)

## Documentary requirements
Annex 10: List of Requirements to Establish the Qualification of the Private Proponent for Unsolicited Proposals
The following documents and information are required to be submitted:
Answer the boxes below. Is the document submitted? (Yes, No, or N/A)
↓
For all entities listed in the Private Proponent Information and Qualification Form
1 | --- | Valid SEC registration (or foreign equivalent)
2 | --- | Latest proof of nationality (e.g., general information sheet (or foreign equivalent) for corporations, passport/birth certificate for individuals)
3 | --- | List of key personnel (and their corresponding experience)
4 | --- | Certification under oath indicating that the entity:
(a) is not included in blacklists issued by any government agency;
(b) has not been found by final judgment to be liable for violating the Anti-Money Laundering Act or for violating statutes that
carry the penalty of disqualification from participating in tenders for government contract; and
(c) has no pending case filed against it by the government or by it against the government, or, should there be any, that such cases
shall not impact the capability of the prospective Private Partner to carry out its obligations under the PPP Project.
Any misrepresentation in the certification under oath shall be a ground to disqualify the private proponent.
5 | --- | Full disclosure of its pending cases, if any, whether by it against the government or filed against it by the government
Any misrepresentation in the certification under oath shall be a ground to disqualify the private proponent.
6 | --- | Documentary proof that the entity have successfully undertaken project/s similar or related to the proposed project
7 | --- | If the entity is a cooperative, proof of registration with the Cooperative Development Authority (CDA)
For the private proponent or consortium
8 | --- | Letter testimonial from a financial institution (authorized by BSP to transact in the Philippines, or has an investment grade foreign currency
credit rating from a reputable agency which has an outstanding rating on the Republic of the Philippines) attesting that:
(a) The private proponent or members of the consortium are banking with them; and
(b) The private proponent and/or members of the consortium are in good financial standing and/or qualified to obtain debt financing
from such financial institution to finance the PPP Project equivalent to the value of the debt requirement in the proposal.
9 | --- | In case of a consortium, an undertaking, in favor of the Implementing Agency, by all consortium members binding themselves to
be jointly and severally liable for the obligations of the Private Partner under the PPP Contract, if awarded.
Such undertaking shall include a provision that if members of the consortium organize themselves as a corporation registered under
Philippine laws, such corporation shall execute such an undertaking binding itself to the rights and obligations of the Private Partner
under the PPP Contract, which shall substitute or be in lieu of the undertaking submitted by the members or participants of the consortium.
10 |  | If undecided on a specific contractor and/or nominated entities:
| --- |  | (a) shortlist of contractors and/or nominated entities; and
| --- |  | (b) corresponding statement of willingness to participate in the project and capacity to undertake the requirements of the project.
For entities who will infuse equity in the proposed PPP project
11 | --- | Most recent audited financial statements
For entities handling any construction activity
12 | --- | Valid PCAB license (or foreign equivalent)

## Sheet16 (hidden)
| Project Cost | a. Construction Performance Security |  | b. Operation Performance Security |  | c. Warranty Security |  | d. Handback Security
| in PHP M | in PHP M | % of Project Cost | in PHP M | % of Project Cost | in PHP M | % of Project Cost | in PHP M | % of Project Cost
DRP | 4788.13 |  | 2% | 100 adjusted in each year to an amount equal to 10% of Gross Revenue accrued during the previous year. |  | 250 |  | (i) the Handback Rectification Amount comprising the aggregate of the cost necessary to deliver the Handback Rectification Works exceeds (ii) the amount of the Operation Performance Security
DRP | 4504.59 |  | 2% | 100 adjusted in each year to an amount equal to 10% of Gross Revenue accrued during the previous year. |  | 250 |  | (i) the Handback Rectification Amount comprising the aggregate of the cost necessary to deliver the Handback Rectification Works exceeds (ii) the amount of the Operation Performance Security
CGY | 12748.35 |  | 2% | 100 adjusted in each year to an amount equal to 10% of Gross Revenue accrued during the previous year. |  | 250 |  | (i) the Handback Rectification Amount comprising the aggregate of the cost necessary to deliver the Handback Rectification Works exceeds (ii) the amount of the Operation Performance Security