## ANNEX A - ICC Guidelines (hidden)
Operations and Maintenance of Bicol International Airport
List of documentary requirements for unsolicited projects pursuant to Section 10.7 of the 2022 BOT Law IRR
No. | Document (should be in searchable format) | Description/Remarks | Agency Remarks (indicate which specific tab/cells/ annex/page(s) the document or information is found) | Evaluator Remarks | Project Name (as stated in document)
1 | Letter of the Agency to the ICC submitting the project for approval | The letter should indicate the following: | Submitted: DOTr_DRP_20230510_1_ DOTr and CAAP Re-endorsement | Document submitted Submitted as "re-endorsement" and as per ICC Guidelines, this should be considered as new project | Operations and Maintenance of Bicol International Airport | "Re-endorsement" letter does not include a description and expected output and outcome, but instead refers to a previous endorsement letter.
|  | a. project name |  | Information provided
|  | b. description |  | Information provided in the annexed letter dated March 22, 2023
|  | c. expected output and outcome |  | Information provided in the annexed letter dated March 22, 2023
|  | d. implementation period |  | Information provided in the annexed letter dated March 22, 2023
|  | e. list of all documents being submitted in support of the project proposal |  | Information provided
|  | f. the full and unqualified endorsement of the Head of the Agency submitting the project for ICC/NEDA Board approval |  | Information provided
2 | Company profile of the project proponent | Pursuant to Sections 10.7, 10.6(c), 10.4(a)(i), a company profile showing the company’s mission, business lines, past and ongoing projects, and, financial highlights shall be submitted. | Submitted: DOTr_DRP_20230510_2_Business Plan DOTr_DRP_20230510_2_Company profile | Document submitted
3 | Complete Feasibility Study (F/S) | Pursuant to Sections 2.7 and 10.4(a)(ii) of the Revised 2022 BOT Law IRR, a complete feasibility study (F/S) should contain information that are up-to-date and are not older than three (3) years as of the date of submission to the Approving Body. The F/S should also contain the following information: | Submitted: DOTr_DRP_20230510_3_Complete Feasibility Study (F-S)_clean DOTr_DRP_20230510_3_Complete Feasibility Study (F-S)_marked | Document submitted | Operations and Maintenance of Bicol International Airport
|  | a. problem definition or statement of objectives | Section 1 | Information provided
|  | b. project description* | Section 1 | Information provided |  |  | This section presents the project’s configuration and scope of works particularly a brief description of the components, the location and the areas of service/influence. This should clearly indicate the outputs (e.g., products, services, target users) of the project.
|  | c. project context in the Agency’s overall strategy/program* | Section 2.6 Project Linkages | Information provided is incomplete No mention of timelines and investment requirement as required in the annexed detailed description of requirements |  | FS mentions the National Transport Policy. No mention of overall development timelines, and investment requirements. | This pertains to the overview of the concerned Department’s national strategy and program, including overall development outcomes, timelines, and investment requirements, and the specific link of the proposed project outputs, timelines and investment requirements to achieve the Department’s national strategy and program.
|  | d. sectoral program context* | Section 2.1, 2.2 | Information provided |  | no linkage with other initiatives in the sector. Section 4.13 of APER discloses the AIC is also the OP for Bohol and Laguindingan. | This section provides a brief overview of sector targets, existing programs and sectoral gaps based on existing master plans/sectoral programs, how the proposed project addresses the needs, priorities and objectives of the sector, and linkage of the proposal with other initiatives in the sector as well as related projects in other sectors.
|  | e. regional and spatial context* | Section 2.1, 2.2 | Information provided |  | provide easy access to the region and connect it to the global market, identifies connectivity as a core strategy | This section indicates the geographical coverage of the proposed project and its linkage with other projects within the region and across the country. For area specific projects, justification for the choice of area/s should be clearly stated. This may include, as annexes, location map and other relevant technical diagrams.
|  | f. expected outcomes and key success indicators, including means of verification and key assumptions | As discussed with TWG, proponent has updated FS and CA to refer to 12th edition. Proponent working with Technical Consultant to do analysis on comparison of 10th and 12th, to check and review possible required updates to the MPSS. | Information provided
|  | g. analysis of technical solutions or alternatives, including analysis of risks and impacts* | Section 3.2 | Information provided
|  | h. stakeholder analysis* | Section 2.10 | Information provided |  | identifies stakeholders. only covers consultations with the Grantor. No "public consultation" done. | The stakeholder analysis should include a discussion on the results of the conducted public consultations, including how concerns are mitigated.
|  | i. project costs* | Section 2.4, 4.2 | Information provided |  | does not specify "cost of chosen technology and mitigating related risks and impacts" | For operations and maintenance PPP projects, the Project Cost refers to the present value of the costs incurred in delivering the contracted service, including any reinvestment requirements as provided in the approved contract. Project cost should also include cost of a chosen technology and mitigating related risks and impacts.
|  | j. legal due diligence, which includes policy and regulatory framework of the market/s affected by the project, and institutional analysis | Section 2.3 | Information provided
|  | k. demand analysis* | Section 3.1 | Information provided |  |  | An analysis of the market as well as the existing and projected demand for the project. This includes assumptions in the demand forecast, the historical data used as basis in the forecast, if any, and an assessment on the appropriateness of project interventions, considering market characteristics (e.g., user fees vs willingness-to-pay).
|  | l. information on the proposed tariff structure | Section 4.5 | Information provided
|  | m. financial analysis (including information on project revenues consistent with the financial model)* | Section 4.6 | Information provided
|  | n. economic analysis (including information on economic benefits and cost consistent with the economic model)* | Section 5 | Information provided
|  | o. project safeguards*  environmental quality  natural and cultural resources sustainability  climate change and hazards  equity in development benefits  health and safety | Section 8 | Information provided
|  | p. risk allocation and risk mitigating plan | Section 7.4 | Information provided
|  | q. value for money analysis* | Section 6.1 | Information provided
|  | r. public-private Partnership (PPP) contractual arrangement options and assessment of the proposed contractual arrangement | Section 1 and 2.3 | Information provided
|  | s. information on job creation (from development to operation and maintenance)/employment impact of the project, and number and types of jobs with corresponding sex-aggregated data and amount of wages/salaries | Section 5.6 | Information provided
4 | Electronic copy of the economic model | Pursuant to Sections 2.7 and 1.3(j) of the Revised 2022 BOT Law IRR, the economic model should: a. be in traceable formula format (assumptions/inputs shall be shown in a summary sheet that are linked to the relevant work sheets of the model) b. contain information that are up-to-date and are not older than three (3) years as of the date of submission to the approving body | Submitted: DOTr_DRP_20230510_4 and 5_Electronic copy of the financial and economic model | Document submitted inputs sheet contains hard coded values for traffic, tariff, revenue sharing, among others. | Bicol International Airport
|  | The economic model should also contain the following: a. economic benefits and costs of a project b. assumptions used in calculating economic benefits, and conversion of financial costs to economic costs c. calculation of economic viability (i.e., economic internal rate of return; economic net present value; benefits-cost ratio) |  | Formula errors |  | error in sensitivity analysis
Moreover, the submission shall consider the current situation, as may be applicable (e.g., impacts of a pandemic on demand and costs)
5 | Electronic copy of the financial model | Pursuant to Sections 2.7, 1.3(l), 2.10(i), 15.2(a)(ii), and 15.2(b) of the Revised 2022 BOT Law IRR, the financial model should: a. be in traceable formula format (assumptions/inputs shall be shown in a summary sheet that are linked to the relevant work sheets of the model) b. contain information that are up-to-date and are not older than three (3) years as of the date of submission to the approving body | Submitted: DOTr_DRP_20230510_4 and 5_Electronic copy of the financial and economic model | Document submitted inputs sheet contains hard coded values for traffic, tariff, revenue sharing, among others.
|  | The financial model should also contain the following: a. projected balance sheet of the project for its full life cycle b. assumptions used in calculating the financial revenues and financial costs c. income statement of the project for its full life cycle d. cash flows statement of a project for its full life cycle e. calculations on financial viability (i.e., free cash flows to firm and equity holders; project and equity internal rates of return; project and equity net present value; weighted average cost of capital; cost of equity components based on Capital Asset Pricing Model (CAPM) f. calculations on bankability (i.e., debt service coverage ratio) g. amounts to be paid and schedule of payments of firm liabilities h. VFM/Public Sector Comparator model |  | Information provided is incomplete cost of equity components based on CAPM calculation and DSCR not provided, but can be derived based on the provided information
Moreover, the submission shall consider the current situation, as may be applicable (e.g., impacts of a pandemic on demand and costs)
6 | Proposed project Parameters Terms and Conditions (PTC) | Pursuant to Section 2.8 of the Revised 2022 BOT Law IRR, the Agency should submit a proposed set of PTCs for the project. The Agency shall submit its Proposed Parameters Terms and Conditions (PTCs) using the following forms: | Submitted: DOTr_DRP_20230510_6_Proposed project PTC |  | Operations and Maintenance of Bicol International Airport
|  | PTC Form 1 (General Parameters, Terms, and Conditions) which includes the general information about the proposed project as outlined in Section 2.8 of the Revised 2022 BOT Law IRR. | Submitted: DOTr_DRP_20230510_6_Proposed project PTC | Document submitted |  | references Draft CA 2.1 states O&M contractual arrangement, APER states OAT contractual arrangement
|  | PTC Form 2 (Actual and potential conflict between the proposed project and other government projects) which includes the Agency’s assessment of the actual and potential conflicts between the proposed project and other government projects. | Submitted: DOTr_DRP_20230510_6_PTC Form 3 | Document submitted
|  | PTC Form 3 (Firm Liabilities*) which includes the following details regarding the proposed government liabilities for the proposed project: a. Proposed government undertakings (GUs) identified in Section 13.3 of the Revised 2022 BOT Law IRR, as may be applicable. Such GUs may include Viability Gap Funding as defined in Section 1.3(ll) and indicated in Section 15.1 of the BOT Law IRR. For proposed GUs that come in the form of Direct Government Subsidy, the valuations of government assets or property as determined by a government financial institution (GFI) or an independent property appraiser (IPA) should be included. b. Government repayments pursuant to Section 12.16 of the Revised 2022 BOT Law IRR | Submitted: DOTr_DRP_20230510_6_PTC Form 3 DOTr defers to the review and observations of the TWG, NEDA-ICC, and OSG on the final CAs. | Document submitted
|  | PTC Form 4 (Proposed Risk Allocation and Contingent Liabilities* of the government) which includes the risk allocation matrix, the possible resulting contingent liabilities for risks taken on by the government, and the proposed risk mitigating measures. PTC Form 4 effectively serves as the risk mitigation plan required under Section 2.8 of the Revised 2022 BOT Law IRR. Section 15.3(b) of the Revised 2022 BOT Law IRR details the following requirements to be included in the plan: a. a list of all risks assumed by the government under the contract b. risks assumed by the Agency c. risk mitigating measures d. estimated costs to be incurred e. target dates to have each measure in place f. appropriate action plan by the Agency to manage each type of risk The contents of the submitted proposed PTCs should be consistent with the contents of the submitted financial and economic models. (See PTC Forms 1-4) | Submitted: DOTr_DRP_20230510_6_Proposed project Parameters Terms and Conditions (PTC) | Document submitted
7 | Agency Project Evaluation Report (APER) | The Agency PER is a summary of the Agency’s due diligence on the proposed PPP project, which should include the following sections: | Submitted: DOTr_DRP_20230510_7_APER | Document submitted | Operations and Maintenance of Bicol International Airport
|  | a. Assessment on the completeness of submission pursuant to Sec 2.7 and 10.4 of the IRR and this ICC Guidelines | Section 3.1 Completeness of Submission | Information provided |  | Pursuant to 10.4.a.iii of the Revised 2022 IRR, lacks an assessment on the consistency of draft contract with Section 4.3 of the Revised 2022 IRR.
|  | b. Assessment of project eligibility with respect to Sections 2.3, 10.1, 10.2, and 10.3 | Section 3.2 Project Eligibility | Information provided is incomplete |  | The APER provides an assessment of project eligibility in terms of presence of a new technology; It does not provide an assessment of project eligibility in terms of: 1. Absence of direct government guarantee,direct government subsidy or direct government equity required 2. Not a component of an approved project
|  | c. Project context in the implementing agency’s overall strategy/program | Section 2.2.2 Project context in the implementing agency’s overall strategy/program | Information provided
|  | d. Assessment of the qualification of the proponent in terms of legal requirements, firm experience or track record, and financial capability | Section 3.3. Qualification of the Proponent | Information provided
|  | e. Assessment of the appropriateness of the chosen contractual arrangement | Section 3.4. Appropriateness of Contractual Arrangement | Information provided |  | For discussion *To consult principals if assessment is valid: "DOTr defers to the review and observations of the TWG, NEDA-ICC, and OSG on the final Concessionaire Agreement xxx"
|  | f. Agency’s findings on the following: i. Technical evaluation ii. Demand analysis iii. Environmental evaluation including climate change resiliency considerations iv. Institutional analysis v. Social analysis including gender safeguard vi. Economic analysis vii. Financial analysis | Section 4. Project Evaluation | Information provided
|  | For the findings on the Economic and Financial analysis, include analysis of robustness and reasonableness of assumptions used in the economic and financial models as discussed in ICC Evaluation Criteria for the Review of Public – Private Partnership Projects For unsolicited proposals whose subject matter is covered by existing comparable feasibility study/ies, the IA may include a comparative evaluation of the level of detail (LoD) between the unsolicited proposal FS and the relevant comparable FS. | No comparable unsolicited proposal and/or feasibility study
|  | g. Information on the proposed tariff structure | Section 5. Proposed Tariff Structure | Information provided
|  | h. Justification of the preferred bid parameter | Section 6. Preferred Bid Parameter | Information provided |  | bid parameter not specified in stated CA section
|  | i. Recommended reasonable rate of return (RROR) | Section 7. Recommended Reasonable Rate of Return (RROR) | Information provided
8 | Valuation report on the valuation of government assets | Pursuant to Sections 13.3(c) of the Revised 2022 BOT Law IRR, a report on the valuation of contributed government assets or property/ies that are to be used/included in the financial model. The valuation shall be as determined by a GFI or by an IPA included in the list of Accredited Asset Valuers of the Securities and Exchange Commission (SEC). The report should not be older than one (1) year from the date of submission to the Approving Body. In case of IPA, proof of the valuation company’s inclusion in the list of Accredited Asset Valuers of the SEC must be also submitted. | Submitted: DOTr_DRP_20230510_8_Valuation report on the valuation of government assets_CAAP DOTr_DRP_20230510_8_Valuation report on the valuation of government assets_DOTr endorsement to COA DOTr_DRP_20230510_8_Valuation report on the valuation of government assets_DOTr | Document submitted
9 | Gender responsiveness checklist | Pursuant to the ICC Memorandum titled “ICC Policy on Integrating the Harmonized Gender and Development Guidelines (HGDG) in the ICC Process” dated September 30, 2016, the Agencies are required to accomplish and submit Gender Responsiveness Checklist (the Combined Generic Checklist for the Project Identification and Design Stages). The guidelines for accomplishing the Gender-Responsiveness Checklist can be accessed at: https://neda.gov.ph/wp- content/uploads/2020/09/Guidelines-in-Accomplishing-the-ICC-PE-on- Gender-Responsiveness-Checklist.pdf | Submitted: DOTr_DRP_20230510_9_Gender responsiveness checklist | Document submitted | Unsolicited Proposal for the New Bicol International Airport
10 | Location map (with e- copy) | A diagram that outlines the project site should include major landmarks and infrastructure/ facilities within the project area. | Submitted: DOTr_DRP_20230510_10_Location map (with e- copy) | Document submitted
11 | Right of Way Acquisition (ROWA)* / Resettlement Action Plan (RAP) or a Certification from the Head of Agency that all project land and other ROW have been acquired (for projects requiring project land or ROW) | A document showing the extent of the project’s ROW requirements and estimated costs. At the minimum, the submitted plan(s) should include the following information: | Not applicable. The Project does not require additional land. | Not applicable
a. Project Affected Persons (PAPs): a) estimated number (PAPs, households); b) profile/group: IPs, owners, ISFs, etc.; c) compensation package, with estimated amount (per PAP or per household), including livelihood program/Social Development Program, if any;
b. Affected structures: a) estimated number; b) type: commercial, residential, government asset, etc. ; c) compensation package, with estimated amount (per affected structure);
c. Utilities (electricity, water, ICT/Telecoms, etc.): a) estimated number; b) type of utility; c) relocation cost, with amount (per affected utility), d. Institutional arrangement (parties involved and their responsibilities); e. Activities and implementation period; and f. Applicable laws, rules and regulations. ROWA and RAP costs must be specified and itemized in the financial model (if the project does not involve an acquisition of land for the project, indicate 0). The ROW and resettlement costs are typically significant expense items that the proponent of an unsolicited proposal must bear. This must be clearly reflected in the PTC and financial model.
12 | Certification from Head of Agency on the conduct of the mandated evaluation pursuant to Section 10.6 of the Revised 2022 BOT Law IRR | Certification from Head of Agency, and supporting documentation, that it has done the mandated evaluation of the unsolicited proposal, pursuant to Section 10.6(c)(i) of the Revised 2022 BOT Law IRR (See prescribed Certification template) | Submitted: DOTr_DRP_20230510_12_Certification from Head of Agency | Document submitted | Operations and Maintenance of Bicol International Airport
13 | Original proponent status (OPS) by the Agency | Copy of the document granting the OPS by the Agency to the private proponent | Submitted: DOTr_DRP_20230510_13_OPS DOTr_DRP_20230510_13_Signed Board Secretary's Certificate DOTr_DRP_20230510_17_Draft CAAP Board Resolution | Document submitted | Operation and Maintenance of the Bicol International Airport | CAAP - Board Resolution granting OPS unsigned, Secretary's Certificate signed
14 | Draft PPP contract | Pursuant to Sections 10.4(a)(iii) of the Revised 2022 BOT Law IRR, the draft contract to be submitted should contain the mandatory terms and conditions set forth in Section 4.3 of the Revised 2022 BOT Law IRR. | Submitted: DOTr_DRP_20230510_14_Draft PPP contract_cover DOTr_DRP_20230510_14_Draft PPP contract DOTr_DRP_20230510_14_Draft PPP contract_annexes DOTr defers to the review and observations of the TWG, NEDA-ICC, and OSG on the final CAs. The draft PPP Contract reflects DOTr as the sole grantor for the Project. However, DOTr and CAAP commit to submitting a revised version of the draft PPP Contract, reflecting DOTr and CAAP as co-grantors, during the evaluation period of the ICC. | Document submitted (Draft contract states only DOTr as grantor and no mention of the CAAP as co-grantor) | Bicol International Airport
15 | Unsolicited Proposal Assessment Forms (USP AFs) | The agency shall fill out the following forms to establish the project proponent’s legal eligibility pursuant to Section 5.4(a), firm experience or track record pursuant to Section 5.4(b), and financial capability pursuant to Section 5.4(c) of the Revised 2022 BOT Law IRR. | Submitted: DOTr_DRP_20230510_15_USP AF5_Unsolicited Proposal Assessment Forms (USP AFs) |  | Operations and Maintenance of Bicol International Airport
| a. USP AF 1: Assessment of the project proponent’s legal eligibility, including proof of legal eligibility | The following proofs of legal eligibility must be submitted by the proponent:  If the proponent is composed of an individual or a group of individuals (including partnerships), but not a corporation, proof of identity of each individual  If the proponent is a corporation - Copy of SEC Registration (Sec. 5.4(a)(i) of the BOT Law IRR) - Copy of completely filled general information sheet (GIS) with proof of receipt by SEC - Sworn certification by the corporate secretary to the authenticity of submitted documents  If the proponent is a consortium - An agreement among members to form a consortium to undertake the project - An undertaking, binding the consortium members to be jointly and severally liable for the obligations of the project proponent under the contract (Sec. 5.4(a)(iv) of the BOT Law IRR) - Shareholder agreement based on proposed ownership structure (Sec. 5.4(c)(i)(1) of the BOT Law IRR)  If the proponent is a cooperative - Copy of CDA Registration (Sec. 5.4(a)(i) (ii) and (iii) of the BOT Law IRR) If the proponent and the operator are two separate independent entities, the nominated operator must submit the following:  If the operator is composed of an individual or a group of individuals (including partnerships), but not a corporation, proof of identity of each individual  If the operator is a corporation - Copy of SEC registration (Sec. 5.4(a)(ii) of the BOT Law IRR) - Copy of completely filled SEC GIS with proof of receipt by SEC - Sworn certification by the corporate secretary to the authenticity of submitted documents  If the operator is a cooperative - Copy of CDA Registration (Sec. 5.4(a)(i) (ii) and (iii) of the BOT Law IRR) For each contractor participating in construction PCAB license if a Filipino company, or its equivalent issued by the country of origin, if a foreign company (Sec. 5.4 (a)(v) of the BOT Law IRR) For projects involving the operations of public utilities, the Filipino citizenship for individuals, and the 60% Filipino ownership or interest, for corporations and consortiums respectively, are required. | Submitted: DOTr_DRP_20230510_15_USP AF1 | Document submitted
| b. USP AF 2: Assessment of the project proponent’s experience or track record, including proof of experience or track record | The proponent by itself or through the member-firms in case of a consortium, or through its Contractor and/or nominated entities must submit the following:  A list of projects similar or related to the proposed project, including information on the asset owner of the project, the location of the project, and the year the project was undertaken. A certification from the asset owner that the entity had successfully undertaken the project or the activity under the project in the list must be submitted.  A list of key personnel and for each personnel, the role in the project, a description of relevant experience and the years of experience in the role provided. A curriculum vitae showing the year, duration, location and nature of experiences relevant to the project should be attached for each personnel.  If the nominated entities are bound by a technical services agreement (TSA), the following must be submitted: o proof that the nominated entities are bound by a TSA o a list of projects similar or related to the project/s to be bid undertaken by the nominated entities that will provide the technical services  If undecided on a specific Contractor and/or nominated entities, the proponent must submit the following: o a short list of Contractors and/or nominated entities from among which it will select from o statements from the short-listed Contractors and/or nominated entities indicating willingness to participate in the project and capacity to undertake the requirements of the proposed project If the proponent is a consortium, the following must also be submitted:  A business plan, containing the following information: o Members of the consortium o Equity interest/contribution of each member to the consortium, their prospective Contractor(s) and/or nominated entities, if the experience of their Contractor(s) and/or nominated entities are necessary for the determination of the capacity of the consortium to undertake the project o Description of the respective roles of the members and Contractors and/or nominated entities in the project, including the prospective facility operator(s), if applicable. | Submitted: DOTr_DRP_20230510_15_USP AF2 | Information provided Information provided for list of personel; Information incomplete for CV |  | a. ok for Aboitiz Construction. Certification for daa issued by daa. b. ok c. willingness to participate - "if awarded, shall formally enter into a contract" |  | - Safety supervisor lacks CV of Noel Tanillon (Name in the CV provided for safety supervisor is different form list of personel)
| c. USP AF 3: Assessment of the project proponent’s financial capability, including proof of financial capability | The following proofs of financial capability must be submitted by the proponent:  Latest audited financial statement of each consortium member from previous reporting period of the period of evaluation (Sec. 5.4 (c)(i)(1) of the BOT Law IRR) For equity  If equity shall be financed through set-aside deposit, proof of set- aside deposit equivalent to the equity requirement of the project from a domestic universal/commercial bank or an international bank that is authorized by the BSP to transact in the Philippines. The document must indicate that the set-aside deposit is committed solely for the project For debt  Letter testimonial from each bank that will provide the debt requirement for the project attesting that :1) the prospective Project Proponent and/or members of the consortium are banking with them; 2) the Project Proponent and/or members of the consortium are in good financial standing and/or are qualified to obtain credit accommodations from such banks, or a statement of similar tenor, to finance the project equivalent to the value of the debt requirement in the proposal. The testimonial must come from a domestic universal/commercial bank or an international bank that is authorized by the BSP to transact in the Philippines. (Sec. 5.4 (c)(ii) of the BOT Law IRR) | Submitted: DOTr_DRP_20230510_15_USP AF2 | Document submitted *(AFS submitted is as of 2021)
| d. USP AF 4: Assessment of the draft contract | This form shall establish the consistency of the draft contract pursuant to Section 4.3 of the Revised 2022 BOT Law IRR. | Submitted: DOTr_DRP_20230510_15_Unsolicited Proposal Assessment Forms (USP AFs) | Document submitted
| For projects with proposed new technology/concept: e. USP AF 5: Assessment of proposed new technology/ concept | The agency shall establish the eligibility of the project pursuant to Section 10.1(a) and 10.2 of the Revised 2022 BOT Law IRR. (See USP Assessment Forms 1-5) | Submitted: DOTr_DRP_20230510_15_USP AF5 | Document submitted
Additional requirement for agencies submitting as an attached agency: a. The full and unqualified endorsement by the Head of Mother Agency should be attached to the cover letter; |  |  | Submitted: DOTr_DRP_20230510_1_ DOTr and CAAP Re-endorsement
Additional requirements for projects with proposed new technology/concept: a. The USP AF 5 (assessment of proposed new technology/concept) should be filled out by the agency b. The following must be submitted: i. Certification from the implementing agency that based on its assessment, the new concept or technology possesses any of the features specified in Section 10.2 of the Revised 2022 BOT Law IRR and other features that would have a positive impact on the implementation and operations of the project. Such certification may also be sought from relevant government agencies/bodies/ institutions/etc., with knowledge of the proposed new concept or technology ii. Details of the new concept or technology and cost-benefit analysis comparing the new concept/ technology with traditional ones iii. Proof that the proponent itself has, through or any of its consortium members or contractors or nominated entities have, directly and successfully implemented the new concept or technology at a scale similar to the proposed project. The information disclosed must be in sufficient detail so as to allow the proper evaluation of the new concept or technology. |  |  | Submitted: DOTr_DRP_20230510_15_USP AF5 | Document submitted | Upgrade, Expansion, Operation and Maintenance of the Bicol International Airport | Listed "Bicol (New Legaspi) International Airport" is construction of airport.
Additional requirements for projects undertaken by Government-Owned and Controlled Corporations: a. Electronic copy of the financial model of the GOCC’s projected cash flows, income statement, and balance sheet without the project, for the duration or life of the project. This should be in traceable format, including relevant assumptions. b. Copy of the Board Resolution, duly signed by the members, approving the proposed project. |  |  | a. DOTr_DRP_20230510_16_Electronic copy of the financial model of CAAP_WITHOUT DRP TAG CGY DOTr_DRP_20230510_16_Electronic copy of the financial model of CAAP_WITH DRP TAG CGY b. DOTr_DRP_20230510_17_Signed Board Secretary's Certificate DOTr_DRP_20230510_17_Draft CAAP Board Resolution | a. Document submitted b. Document not submitted | Operation and Management of the Bicol International Airport | financial model without the project: 1. Income Statement row 140 - hardcoded amounts 2. interest income 35 yrs row 9, 23 - hardcoded amounts - exchange rate (Sheet 2, C7)

## PTC Form 1
Annex 8: PTC Forms
PTC Form 1: Proposed General Parameters, Terms, and Conditions
Legal Bases: |  | Section 7(c) of the PPP Code, and Section 30 of its IRR
Objective: |  | To establish the parameters, terms, and conditions (PTCs) of the proposed PPP project to be set forth by the Approving Body
Instructions: |  | 1. In column G of the matrix below, provide sufficient details of the proposed PTC to the extent that it will aid the decision of the Approving Body. 2. In case a listed PTC does not apply to the project concerned, indicate "Not applicable" in column G of the matrix below. 3. Details of the PTCs provided in the matrix below must be consistent with the financial model and the draft contract. 4. The IA shall answer all PTC Forms and each of its questions squarely and clearly. 5. References to external documents must not be made except for references to laws, rules, guidelines, issuances and other similar documents.
Official Project Name
1. Proposed PTCs for the proposed PPP project
| Group No. | Item No. | PTCs |  |  | Describe the proposed PTC to the extent that will aid the detailed evaluation of the IA
| 1 | 1.1 | Scope of the project | Construction | What assets shall be constructed?
|  | 1.2 |  | Supply | What assets shall be supplied?
|  | 1.3 |  | Operation | Shall operation be part of the scope? If yes, what operation activities are included?
|  | 1.4 |  | Maintenance | Shall maintenance be part of the scope? If yes, what maintenance activities are included?
|  | 1.5 |  | Capacity augmentation/expansion/ extension | Shall capacity augmentation/expansion of the system, or extension of alignment be part of the scope? If yes, what augmentation/expansion/extension activities are included?
|  | 1.6 |  | Financing | Which elements shall be financed by the private sector?
|  | 1.7 |  |  | What is the maximum Debt-to-Equity ratio allowed for this project?
| 2 | 2.1 | Estimated Project Cost | Estimated Project Cost as defined in the PPP Code and its IRR | What is the estimated project cost?
| 3 | 3.1 | Contractual arrangement | Contractual arrangement | What shall be the contractual arrangement of the project?
| 4 | 4.1 | Term | Contract duration | How long shall the contract be in effect?
|  | 4.2 |  | Contract effectivity | When shall the contract be effective?
| 5 | 5.1 | Bid Parameter | Bid parameter | What is the proposed bid parameter for the project?
| 6 | 6.1 | General performance standards and targets | Capacity | What shall be the required capacity of the project? E.g., No. of passengers per year (for airport), or no. of patients per day (for hospital project)
|  | 6.2 |  | Quality performance specifications | What shall be the performance standards and targets for: a) environmental quality b) natural and cultural resources sustainability c) climate change and hazards, and environmental considerations d) equity in development benefits, including GEDSI e) health and safety f) service quality g) asset quality h) safeguards that will protect the interests of the government and the public
|  | 6.3 |  | Other performance specifications | What are the other performance specifications of the project?
| 7 | 7.1 | Obligations related to constuction & supply of assets | Delivery of project site/right-of-way (ROW) | What government assistance needed for securing project site/ROW?
|  | 7.2 |  |  | If an unsolicited project, how shall the implementing agency be compensated?
|  | 7.3 |  | Assets to be constructed/supplied by the private proponent | Of the total assets to be constructed (see Item No. 1.1 above), what assets shall be constructed by the private proponent?
|  | 7.4 |  |  | Of the total assets to be supplied (see Item No. 1.2 above), what assets shall be supplied by the private proponent?
|  | 7.5 |  | Assets to be provided by the implementing agency | What assets shall be supplied by the implementing agency?
|  | 7.6 |  |  | If an unsolicited project, how shall the implementing agency be compensated?
|  | 7.7 |  |  | Under what conditions will the transfer of the asset occur? (e.g., as-is-where is basis)
|  | 7.8 |  | Assets to be constructed/supplied by the incorporated JV | Which assets shall be provided/constructed by the Incorporated JV?
|  | 7.9 |  | Failure to meet obligations | What are the consequences/penalties for failure to meet obligations related to supply of assets by the implementing agency?
|  | 7.10 |  |  | What are the consequences/penalties for failure to meet obligations related to construction / supply of assets by the private proponent?
| 8 | 8.1 | Obligations related to operation | Assignment of responsibility for operations | Of the operations in Item No. 1.3, which shall be under the private proponent's responsibility?
|  | 8.2 |  |  | Shall the above include commercial operations? If yes, what shall be allowed?
|  | 8.3 |  |  | Of the operations in Item No. 1.3, which shall be under the implementing agency's responsibility?
|  | 8.4 |  | Failure to meet obligations | What are the consequences/penalties for failure to meet obligations related to operations by the private proponent?
| 9 | 9.1 | Revenues going to the private proponent | Tariffs paid by users | What Tariffs will be charged for the project?
|  | 9.2 |  |  | How much shall be the Tariffs at the start of operation?
|  | 9.3 |  |  | What shall trigger the adjustment of Tariffs?
|  | 9.4 |  |  | What shall be the formula for the adjustment of Tariffs?
|  | 9.5 |  | Payments coming from the agency | Are there payments coming from the government (e.g. availability payments, milestone payments, amortization payment)? If yes, ensure that details are provided in PTC Form 2.
|  | 9.6 |  | Other sources of revenues | What other sources of revenues will be available to the private proponent?
| 10 | 10.1 | Revenues going to the implementing agency | Share in project revenues | Which of the project revenues shall be shared with the implementing agency?
|  | 10.2 |  |  | How much shall be the implementing agency's share?
|  | 10.3 |  | Other Payment/s to the implementing agency | Are there other payments/revenues that will accrue to the implementing agency?
|  | 10.4 |  |  | What is the schedule of the payments to be made by the private proponent (amount of each payment, due date)?
| 11 | 11.1 | Transfer at the end of the contract | Assets to be transferred | What assets shall be transferred to the implementing agency?
|  | 11.2 |  |  | What shall be the required condition of the assets when transferred to the implementing agency?
|  | 11.3 |  |  | Who shall shoulder costs related to transfer of assets to the implementing agency?
| 12 | 12.1 | Public bidding process and comparative challenge process | Manner and period of the public bidding process or comparative challenge process | How shall the public bidding process or comparative challenge process be conducted (single-stage or two-stage bidding)?
|  | 12.2 |  |  | For unsolicited proposals, how long shall the period for the comparative challenge process be (i.e., not less than ninety (90) calendar days and not more than one (1) year)?
| 13 | 13.1 | Contract variation | Allowable variations for the project | What are the allowable variations for the project?
|  | 13.2 |  | Thresholds/limitations on contract variations | What shall be the thresholds/limitations on the following variations, if allowed under Item 13.1? -Changes in the approved scope of works, decrease in the performance standards, deferment of committed service levels, or change in the contractual arrangement; -Extension in the contract term -Variation that will result in an increase in the financial liabilities of the government
| 14 | 14.1 | Joint Ventures | Type of JV | Will the project be undertaken through a contractual JV or a JV Company?
|  | 14.2 |  | Government Undertakings | What are the Government Undertakings, including equity contribution and other allowable Government Undertakings for the JV?
|  | 14.3 |  | Private proponent contribution | What will be the required equity contribution from the private proponent? What is the total amount of this contribtuion?
|  | 14.4 |  | Profit sharing | What is the proposed profit sharing between the implementing agency and the private proponent?
| 15 | 15.1 | Other major government obligations | Other major government obligations | What other major obligations shall the government undertake for the project (e.g., assurance of no competing facilities, etc.)?
| 16 | 16.1 | Other PTCs | xxx | xxx
|  | 16.2 |  | xxx | xxx
2. Other PTCs to be threshed out in the PPP contract
a. The following PTCs shall be part of the terms of the contract, and the implementing agency is given the authority to finalize the terms during contract drafting, subject to the review of relevant authorities.
| Group No. | Item No. | PTC
| 1 | 1.1 | Start of concession | If a concession agreement, event that shall trigger the start of the concession.
| 2 | 2.1 | Implementation milestones | Implementation milestones, including those for securing other approvals, period within which Financial Close shall be achieved by the proponent, and the project completion date.
| 3 | 3.1 | Performance Security | The project shall require the following performance securities for each stage of project implementation, as applicable:
a. Construction Performance Security
b. Operation Performance Security
c. Warranty Security
d. Handback Security
|  | 3.2 |  | For each security, the contract shall identify the form, which may be any or a combination of the following:
a. Cash
b. Bank draft or guarantee confirmed by a local bank (in the case of foreign bidders bonded by a foreign bank)
c. Letter of credit issued by a reputable bank
d. Surety bond callable on demand issued by the GSIS or by surety or insurance companies duly accredited by the office of the Insurance Commissioner
|  | 3.3 |  | The amount of each security to be set by the agency.
| 4 | 4.1 | Contingent Liabilities | Contingent liabilities to be assumed by the government for the project as listed in PTC Form 4, including all other contingent liabilities to be assumed by the government that are present in the project but not covered in PTC Form 4, shall be transparent in the contract and shall contain the following information, as applicable:
a. Specific risk events that would trigger such liabilities
b. The probability or likelihood that such risks will occur
c. A condition to negotiate a remedy or cure for a risk event
d. A term for curing period
e. The manner of compensation for the economic impact on the Project Proponent, if compensation is financial
f. The method or principle of calculation of financial compensation
g. The materiality threshold
h. The cap on compensation
i. A condition to include step-in rights
j. Parameters for payments if terminated
| 5 | 5.1 | Obligations related to constuction & supply of assets | Procedure for handover of project site/right-of-way (ROW)
|  | 5.2 |  | Representatives of parties in the group that will monitor the progress of construction
|  | 5.3 |  | Roles and responsibilities of the representatives from each party
|  | 5.4 |  | Condition of the assets that will be handed over by the agency to the proponent
|  | 5.5 | Obligations related to operation | Representatives of parties in the group that will monitor the performance during operation
|  | 5.6 |  | Roles and responsibilities of the representatives from each party
| 6 | 6.1 | Revenues going to the agency | Accounting for fees, tolls, charges paid by users collected by the proponent on behalf of the agency
|  | 6.2 |  | Procedures for remittance of such fees, tolls, charges paid by users to the agency
|  | 6.3 |  | Accounting for revenues that shall be shared by the proponent with the agency, if any
|  | 6.4 |  | Procedures for remittance of such revenues to the agency
|  | 6.5 |  | Accounting for government share in the upside, if such revenues be shared with the government
|  | 6.6 |  | Procedures for remittance of such revenues to the agency
| 7 | 7.1 | Other obligations of the parties | Acceptance tests and procedures
|  | 7.2 |  | Kinds of assistance needed from agency, if any
|  | 7.3 |  | Compensation for providing such assistance, if such assistance shall be compensated
|  | 7.4 |  | For contingent liabilities arising from risks:
|  | 7.5 |  | a. Private proponent's compensation for contingent liabilities
|  | 7.6 |  | b. Source of fund in case of monetary payments of contigent liabilities
|  | 7.7 |  | c. If the agency shall avail of the PPP Risk Management Fund
|  | 7.8 |  | Loan or financing documents that will be executed by proponent with its lender for the project
|  | 7.9 |  | Manner by which the private partner discloses its loan or financing documents to the agency
| 8 | 8.1 | Lock-in period or the holding conditions for the proponent | Lock-in period or the holding conditions which the proponent cannot sell the ownership, rights, or interest in the PPP project, if applicable
| 9 | 9.1 | Insurance | Minimum risk insurance coverage as may be required for the project, such as Contractors' all risk, motor vehicle, workforce's compensation, third party liability, force majeure, or comprehensive general liability insurance, as may be applicable.
| 10 | 10.1 | Lender step-in rights | Conditions and procedures for lender step-in rights
| 11 | 11.1 | Permitted security interest | Conditions for acceptable permitted security interest
| 12 | 12.1 | Resolution of corruption | Manner and procedures for resolution of corruption
| 13 | 13.1 | Applicable laws, rules, and regulations | Compliance with applicable laws, rules, and regulations
| 14 | 14.1 | Dispute avoidance and Alternative Dispute Resolution (ADR) mechanisms | Use of dispute avoidance and Alternative Dispute Resolution (ADR) mechanisms pursuant to RA No. 9285 or the "Alternative Dispute Resolution Act of 2004"
| 15 | 15.1 | Ownership and retention of patents, technology and consultant reports | Manner and procedures for ownership and retention of patents, technology and consultant reports
| 16 | 16.1 | Contract termination | Termination Payment Formula formulated in accordance with the guidelines issued by the PPPGB
a. implementing agency
b. private proponent
c. Force majeure and other no-fault termination events
d. Other termination events
|  | 16.2 |  | Events of contract termination for the:
a. Agency
b. Proponent
c. Force majeure and other no-fault termination events
d. Other termination events
|  | 16.3 |  | Other provisions related to events that may lead to Termination including the following:
a. remedies, curing periods
b. lender step-in rights
c. remittance procedures, default interest rates
d. written notice requirements
b. In accordance with relevant laws/issuances, the submission of the document below shall be required, as applicable, on the deadline prescribed by the Approving Body.
| Group No. | Item No. | Parameter, term, or condition
| 1 | 1.1 | Environmental Impact Statement (EIS)/ Environmental Compliance Certificate/ Certificate of Non-Coverage | The proponent shall secure other necessary approvals such as environmental clearances from the DENR. The ICC Project Evaluation Procedures and Guidelines requires to ensure that the project does not adversely affect the environment and/or that appropriate measures are taken to protect the environment.
For environmentally critical projects or projects located in environmentally critical area, the Environmental Compliance Certificate (ECC) shall be a condition precedent to construction start.
|  | 1.2 |  | For non-environmentally critical projects or projects that are not located in environmentally critical areas, the Certificate of Non- Coverage (CNC) shall be obtained and submitted prior to the implementation of the project.

## PTC Form 2
Annex 8: PTC Forms
PTC Form 2: Government Undertakings, and Other Financial Obligations of the Government
Legal Bases: |  | Sections 3(gg), 7(a)(1)(ii)(5), 10(c), and 11(b) of the PPP Code, and Sections 4(fff), 24.4(e), 50, and 103(c)(iii) of its IRR
Objectives: |  | 1) To establish whether the proposed government undertakings are compliant and within the allowable thresholds indicated in the above legal bases
2) To disclose other financial obligations of the government for the project
Official Project Name
Solicited or Unsolicited project? (Solicited/Unsolicited)
Joint Venture (JV) project? (Yes/No)
National or local project? (National/Local)
1. Government undertakings (GU)
a. List all GUs proposed for the project and the estimated value of each GU (sorted by type of GU)
| Type of GU (refer to Section 4 of its IRR for the definition of each type) |  | Specific details of the proposed GU | Specify type of GU in the form of a Subsidy, or a contribution to a JV | Value of each GU | Source/reference for the indicated value of the GU1 | Nature of compensation | Value of compensation for each GU to be paid by the proponent to the government2 | Net estimated value of Subsidy
| 1 | --- |  | --- |  |  |  |  | 0
| 2 | --- |  | --- |  |  |  |  | 0
| 3 | --- |  | --- |  |  |  |  | 0
| 4 | --- |  | --- |  |  |  |  | 0
| 5 | --- |  | --- |  |  |  |  | 0
| 6 | --- |  | --- |  |  |  |  | 0
| 7 | --- |  | --- |  |  |  |  | 0
| 8 | --- |  | --- |  |  |  |  | 0
| 9 | --- |  | --- |  |  |  |  | 0
| 10 | --- |  | --- |  |  |  |  | 0
|  | Total |  |  | 0 |  |  | 0
1 Corresponding source/reference documents for the indicated value of the GU must be included in the submission 2 Section 10(c) of the PPP Code, and Section 50 of its IRR, provide that payment of ROW related costs and contribution of assets, properties, and rights may be allowed in unsolicited proposals if the government receives appropriate compensation, which shall in no way be lower than the value of the costs of ROW to be acquired and the usufruct of assets, properties, and rights contributed
b.i. FOR NON-JV PROJECTS: Assessment on whether the total value of Subsidy does not exceed the threshold set under Section 3(gg) of the PPP Code, and Section 4(fff) of its IRR
| Item |  | Amount
Total Project Cost
| Threshold for Subsidy falling under types 1 and 2 (50% of total project cost)3 |  | 0
| Total Estimated Value of Subsidy falling under types 1 and 2 |  | 0
| Less: Value of Compensation of Subsidy falling under types 1 and 2, if any |  | 0
| Net Estimated Value of Subsidy |  | 0
| % to Total Project Cost |  | #DIV/0!
3 Section 3(gg) of the PPP Code, and Section 4(fff) of its IRR, provides that subsidy falling under items 1 and 2 in the same sections shall not exceed fifty percent (50%) of the Project Cost
b.ii. FOR JV PROJECTS: Assessment on whether the total value of the implementing agency (IA)'s equity contribution, including contribution of assets, properties, and rights, and other allowable GUs do not exceed the set threshold under Section 11(b) of the PPP Code and Section 103(c)(iii) of its IRR
| Item |  | Amount
Total Project Cost (for contractual JV) / Outstanding Capital Stock (for JV company)
| Threshold for IA's contribution in the JV in the form of equity conributions and other allowable government undertakings4 |  | 0
| Total Estimated Value of IA's contribution in the JV in the form of equity conributions and other allowable government undertakings |  | 0
| % to Total Project Cost |  | #DIV/0!
4 Section 11(b) of the PPP Code, and Section 103(c)(iii) of its IRR, provides that the total value of IA's equity contribution, including contribution of assets, properties, and rights, and other allowable GUs shall not exceed 50% of the Project Cost (for contractual JV) or 50% of outstanding capital stock (for JV company)
b.iii. FOR NATIONAL JV PROJECTS: Assessment on whether the total value of the IA's equity contribution, including contribution of assets, properties, and rights, and other allowable GUs, exceeds the set threshold for ICC approval under Section 7(a)(1)(ii)(5) of the PPP Code and Section 24.4(e) of its IRR
| Item |  | Amount
IA's asset position
As of 2025
As of 2024
As of 2023
Latest audited financial statement
| Threshold for IA's contribution in the JV5 |  | 0
| Total Estimated Value of IA's contribution in the JV |  | 0
| % to IA's asset position as of the latest audited financial statements |  | 0%
5 Section 24.4(e) of the PPP Code IRR provides that if the contribution of an IA exceeds 50% of its entire assets, based on either the average of its values for the last three (3) years or the latest audited financial statement, whichever is lower, the proposed National PPP Project shall be approved by the ICC.
2. Other Financial Obligations of the Government
| Type of financial obligation6 |  | Description | Mode of payment | Total Nominal Amount (in PhP) | Source/s of funding | Schedule (Month/Year) | Amount to be paid on scheduled payment
1
2
3
4
5
6
7
8
9
10
|  | Total |  |  | 0 |  |  | 0
6 Financial obligations of the government include Availability payments, Amortization payments after construction of the infrastructure under BT, BTO & BGTOM arrangements, Lease payments under BLT arrangements, Share in the cost of an independent consultant, Cost of acquiring and delivering the right of way, Construction works or cost of construction works assumed by the IA, Capex costs assumed by the IA, among others.
---
|  | VGF and other forms of subsidy |  | Performance undertaking
|  | Payment of ROW related costs |  | Additional exemptions from any tax other than those provided for by law
|  | Performance undertaking |  | Guarantee on Demand
|  | Additional exemptions from any tax other than those provided for by law |  | Guarantee on Loan Repayment
|  | Guarantee on Demand |  | Guarantee on Private Sector Return
|  | Guarantee on Loan Repayment |  | Credit Enhancements
Guarantee on Private Sector Return
|  | Government Equity |  | VGF and other forms of subsidy
|  | Credit Enhancements |  | Performance undertaking
|  | Contribution of assets, properties, and rights |  | Additional exemptions from any tax other than those provided for by law
Guarantee on Demand
|  | --- |  | Guarantee on Loan Repayment
|  | 1- defray, pay for, or shoulder a portion of the Project Cost or the expenses and costs on operating or maintaining the project |  | Guarantee on Private Sector Return
|  | 2- bear a portion of capital expenditures associated with the establishment of an infrastructure or development projects and services |  | Government Equity
|  | 3- contribute any property or assets to the project |  | Credit Enhancements
4- waive charges or fees relative to business permits or licenses that are to be obtained for the Construction of the project
N/A

## PTC Form 3
Annex 8: PTC Forms
PTC Form 3: Proposed Risk Allocation and Risk Mitigation Plan
Legal Bases: Section 7(b) of the PPP Code and Section 28(k), and 55(c) of its IRR
Objective: 1) To identify the proposed risk allocation between the private proponent and the government
2) To identify the probability of risks, mitigating measures, and estimated costs
Official Project Name
1. Proposed Risk Allocation of Risks Identified in GPRAM and the Corresponding Contingent Liabilities (CLs) of the Government
For risks that will be assumed by the GOVERNMENT
| Item No. | Type of Risk | Details of the risk | As per GPRAM issued Aug. 2016, who should take the risk ? G - gov't P - proponent P&G - gov't & proponent | For the Project, who shall take the risk? G - gov't P - proponent P&G - gov't and proponent | Details of the position on each risk including key risk factors and justifications for risk allocations deviating from GPRAM | Who shall assume the risk within the government? (Implementing Agency or National Government) | Probability that such risk will occur | Will this risk expose the goverment to fiscal or financial obligations (CLs)? (if yes, answer suceeding columns) | Specific risk event that would trigger a CL | Risk mitigating measure/ appropriate action plan to manage each type of risk | Estimated cost in implementing the risk mitigating measure | Target dates to have each measure in place
| 1 | Existing structure and assets (refurbishment / extensions) | Risk that existing structures (e.g., buildings, rail lines) and other assets (e.g., computer systems) are inadequate to support new improvements or structures / activities subject of or involved in PPP contract, resulting in additional construction, time, and cost that may be necessary to replace, strengthen, or improve the existing structures or assets to enable it to successfully support the project | P&G |  |  | --- | --- | ---
| 2 | Existing facilities: Current service contracts | Uncertainties inherent in existing contracts for the delivery, upkeep or refurbishment of the asset lead to unexpected benefits or costs for the proponent and/or interface issues | P&G |  |  | --- | --- | ---
| 3 | Existing facilities: Current Government employees | Risks relating to uncertainties and costs in utility of current employees and in retrenching redundant employees | G |  |  | --- | --- | ---
| 4 | Geotechnical site conditions | Risk that unanticipated adverse geological conditions (geotechnical risk) are discovered which cause construction or maintenance costs to increase and/or cause construction delays | P&G |  |  | --- | --- | ---
| 5 | Permits and approvals / Site preparation | Risk that necessary approvals may not be obtained or may be obtained only subject to unanticipated conditions, which have adverse cost and time consequences (e.g. prolonged delay) | P&G |  |  | --- | --- | ---
| 6 | Environmental liabilities existing prior to the project | Risk that the project site is contaminated requiring significant remediation expenses | P&G |  |  | --- | --- | ---
| 7 | Environmental liabilities created during operation | Risk that the use of the facility / project site over the contract term has resulted in significant environmental liabilities (clean up or rehabilitation required to make the site fit for future anticipated use) | P |  |  | --- | --- | ---
| 8 | Cultural heritage | Risk of costs and delays associated with the discovery of archaeological and cultural heritage attributable directly to the Government’s mandated process of conserving, protecting, regulating, and disposition of said discovery | P&G |  |  | --- | --- | ---
| 9 | Availability of site | (i) Risk that tenure / access to a selected site which is not presently owned by Government or proponent cannot be negotiated (ii) Risk of costs and delays in negotiating land acquisition | P&G |  |  | --- | --- | ---
| 10 | Design / Technical risk | Risk that the design of the facility is substandard, unsafe, or incapable of delivering the services at anticipated cost and specified level of service (often resulting in long term increase in recurrent costs and long term inadequacy of service) | P&G |  |  | --- | --- | ---
| 11 | Interconnectivity risk | Interconnectivity refers to the physical linkage of a project to another or to part of a network | P&G |  |  | --- | --- | ---
| 12 | Inter-operability risk | Interoperability risk refers to the risks associated with achieving clear and efficient operational arrangements with other facility operator/s which have to be considered in the project design and operation system requirements | P&G |  |  | --- | --- | ---
| 13 | Construction | Risk that events occur during construction that prevent the facility from being delivered on time and on cost | P |  |  | --- | --- | ---
| 14 | Commissioning | Risk that either the physical or the operational commissioning tests which are required to be completed for the provision of services to commence, cannot be successfully completed | P |  |  | --- | --- | ---
| 15 | Interest rates prior to construction completion | Risk that prior to completion, interest rates may move adversely | P |  |  | --- | --- | ---
| 16 | Interest rates post-completion of construction | Risk that after completion, interest rates may move adversely | P |  |  | --- | --- | ---
| 17 | Exchange rate | Risk that during operation, exchange rates may move adversely, affecting the proponent’s ability to service foreign denominated debt and obtain its expected profit | P |  |  | --- | --- | ---
| 18 | Inflation | Risk that value of payments received during the term is eroded by inflation | P&G |  |  | --- | --- | ---
| 19 | Financing unavailable | Risk that when debt and/or equity is required by the private firm for the project, it is not available then and in the amounts and on the conditions anticipated | P |  |  | --- | --- | ---
| 20 | Sponsor risk | Risk that the proponent is unable to provide the required services or becomes insolvent | G |  |  | --- | --- | ---
| 21 | Change in ownership | Risk that a change in ownership or control of the proponent results in a weakening in its financial standing or support or other detriment to the project | P&G |  |  | --- | --- | ---
| 22 | Tax changes | Risk that before or after completion, the tax impost on the proponent, its assets or on the project, will change | P&G |  |  | --- | --- | ---
| 23 | Lessee risk | Risk that the major critical assets necessary for the operational stage of the project are acquired through leases and that the proponent defaults on those lease obligations. This leads to the assets being foreclosed and the operations of the project being interrupted | P |  |  | --- | --- | ---
| 24 | Inputs / Operating cost overrun | Risk that required inputs during the operations stage cost more than anticipated, are of inadequate quality or are unavailable in required quantities | P |  |  | --- | --- | ---
| 25 | Maintenance and refurbishment | Risk that design and/or construction quality is inadequate resulting in higher than anticipated maintenance and refurbishment costs | P |  |  | --- | --- | ---
| 26 | Changes in output specification outside agreed specification range (including modifications and augmentations) | Risk that Government’s output requirements are changed after contract signing whether pre or post commissioning Change prior to commissioning may require a design change with capital cost consequences depending on the significance of the change and its proximity to completion Change after completion may have a capital cost consequence or a change in recurrent cost only (for example, where an increase in output requirements can be accommodated within existing facility capacity) | P&G |  |  | --- | --- | ---
| 27 | Operator failure / shortfall in service quality | Risk that a subcontract operator may fail financially or may fail to provide contracted services to specification (Failure may lead to service unavailability and a need to make alternate delivery arrangements with corresponding cost consequences) | P |  |  | --- | --- | ---
| 28 | Technical obsolescence or innovation | Risk that the nature of the contracted service or its method of delivery is not keeping pace, from a technological perspective, with competition and/or public requirements Proponent’s revenue may fall below projections either via loss of demand (user pays model) to competing services and/or operating costs increasing Government may wish to change specifications of contracted service | P&G |  |  | --- | --- | ---
| 29 | Third party liability | Risk that third parties file suits or claim damages against Government for faults of the proponent and vice versa | P&G |  |  | --- | --- | ---
| 30 | Demand risk | Risk that operating revenues fall below forecast as a result of decrease service volume (i.e., traffic volume, water or power consumption) attributable to an economic downturn, competition in the relevant market tariff increases, or change in consumer habits | P&G |  |  | --- | --- | ---
| 31 | Changes in competitive network | Risk that an existing network is extended / changed / re-priced so as to increase competition for the facility | P |  |  | --- | --- | ---
| 32 | Ancillary commercial businesses | Risk that ancillary commercial business operations adversely impact the proponent’s fulfilment of PPP contractual obligations and/or pose additional exposures for Government | P |  |  | --- | --- | ---
| 33 | Industrial relations | Risk of strikes or industrial action causing delay and cost to the project | P |  |  | --- | --- | ---
| 34 | Approvals | Risk that additional necessary approvals required during the course of the project cannot be obtained | P&G |  |  | --- | --- | ---
| 35 | Changes in Law / Policy | Risk of a change in law / policy of Government only, which could not be anticipated at contract signing and which has adverse effects on revenues, capital expenditure or operating cost of the proponent | P&G |  |  | --- | --- | ---
| 36 | Economic Regulation | Risk that where there is a statutory economic regulator involved there are pricing or other changes imposed on the proponent which do not reflect its investment expectations | G |  |  | --- | --- | ---
| 37 | Availability of Government Appropriations | Risk in delays in Government contractual payments to the proponent arising from unavailability of Government budgetary appropriations | G |  |  | --- | --- | ---
| 38 | Changes in statutory rates of general application | Risk of changes in minimum wages and other regulated rates of general application affecting the proponent | P |  |  | --- | --- | ---
| 39 | Force majeure risk | Risk that inability to meet contracted service delivery (pre or post completion) is caused by reason of force majeure events | P&G |  |  | --- | --- | ---
| 40 | Default and termination | Risk of ‘loss’ of provision by the proponent of contracted services upon the premature termination of project contract | P&G |  |  | --- | --- | ---
| 41 | Residual value on transfer to Government | Risk that on expiry or earlier termination of the services contract the asset is not in the required condition term | P |  |  | --- | --- | ---
2. Proposed Risk Allocation of other Risks Identified and the Corresponding Contingent Liabilities (CLs) of the Government
For risks that will be assumed by the GOVERNMENT
| Item No. | Type of Risk | Details of the risk | For the Project, who shall take the risk? G - gov't P - proponent P&G - gov't and proponent |  | Details of the position on each risk | Who shall assume the risk within the government? (Agency/LGU or National Government) | Probability that such risk will occur | Will this risk expose the goverment to fiscal or financial obligations (CLs)? (if yes, answer suceeding columns) | Specific risk event that would trigger a CL | Risk mitigating measure/ appropriate action plan to manage each type of risk | Estimated cost in implementing the risk mitigating measure | Target dates to have each measure in place
| 1 | Other risk identified |  |  |  |  | --- | --- | ---
| 2 | Other risk identified |  |  |  |  | --- | --- | ---
| 3 | Other risk identified |  |  |  |  | --- | --- | ---

## PTC Form 4
Annex 8: PTC Forms
PTC Form 4: Identified Interconnection and Interface Risks, and Mitigating Measures
Legal Bases: Section 30(e) of the PPP Code and Section 22 of its IRR
Objectives: | 1) To identify actual and potential interconnection and interface risks between the proposed project and other government projects, if any.
2) To identify plan/measures to address all interconnection and/or interface risks between and among relevant facilities.
3) To serve as basis when crafting the Memorandum of Agreement (MOA) containing an interconnection/interface plan agreed upon by relevant parties.
Official Project Name
1. Does the project has any interconnection or interface risk?
If no, there is no need to answer the table below.
If yes, provide the required details in the table below. For projects with multiple interconnection/interface issue with the proposed subject project, provide the specific details in separate rows, as needed.
a. If the proposed subject project or a significant part thereof has an interconnection/interface risks that fall under any of the following conditions, fill-out the table below:
i. The proposed subject project or a significant part thereof has the same alignment or site with the other project/s
ii. The proposed subject project or a significant part thereof has the same catchment area with the other project/s
iii. The proposed subject project caters to affected markets or groups such that it may negatively affect the economic benefits, demand, and/or financial viability of the other project/s
| Project name | Type of facility | Status | Concerned entity/ies of the relevant facility | Nature of the interconnection/ interface | Specific details of the interconnection and/or interface | What is the proposed plan to address the identified interconnection or interface?
|  | --- | ---
|  | --- | ---
|  | --- | ---
|  | --- | ---
|  | --- | ---
b. If the proposed subject project or a significant part thereof has interconnection/interface risks that do not fall under the conditions provided in (a) above, fill-out the table below:
| Project name | Type of facility | Status | Concerned entity/ies of the relevant facility | Nature of the interconnection/ interface | Specific details of the interconnection and/or interface | What is the proposed plan to address the identified interconnection or interface?
|  | --- | ---
|  | --- | ---
|  | --- | ---
|  | --- | ---
|  | --- | ---
No
Yes
Check Box 11
Check Box 10
Check Box 9
Check Box 8
Check Box 7
Check Box 6
Check Box 5
Check Box 4
Check Box 3
Check Box 2
Check Box 1
No
Yes
Check Box 1
Check Box 2
Check Box 3
Check Box 4
Check Box 5
Check Box 6
Check Box 7
Check Box 8
Check Box 9
Check Box 10
Check Box 11
Yes
No

## PTC Form 5
Annex 8: PTC Forms
PTC Form 5: Mandatory Provisions in the Draft PPP Contract
For unsolicited proposals
Legal bases: See column "PPP Code/IRR Section" (Column D) of the table below.
Objectives: To ensure that mandatory provisions in a PPP contract, pursuant to the PPP Code and its IRR, are included in the submitted draft contract
Official Project Name
No. | Provisions that are explicitly required to be included in the draft contract | PPP Code/ IRR Section | Identify the section/s in the draft contract that pertains to the provision
1 | Specific contractual arrangement, term, and scope of work | Section 84, PPP Code IRR
2 | Minimum performance standards and specification | Section 84, PPP Code IRR
3 | KPIs, targets, and procedures for measuring and reporting results, including dimensions of gender equality, disability and social inclusions (GEDSI) | Section 84, PPP Code IRR
4 | Implementation of milestones, including those for securing other approvals, period within which Financial Close shall be achieved by the Private Partner, and the project completion date Failure to achieve Financial Close within such period, without the fault of the government, shall subject the Private partner to penalties under the signed PPP Contract. | Section 84, PPP Code IRR
5 | Cost recovery scheme via proposed Tariff, as the case may be | Section 84, PPP Code IRR
6 | Obligation of the Private Partner to disclose loan or financing documents, as required under the PPP Code IRR | Section 84, PPP Code IRR
7 | Liquidated damages as contemplated under the PPP Code IRR | Section 84, PPP Code IRR
8 | Performance security requirements, including their validity and top-up mechanism procedures, contemplated under the PPP Code IRR | Section 84, PPP Code IRR
9 | Minimum insurance coverage as may be required for the project, such as Contractors’ all risk, motor vehicle, workforce’s compensation, third party liability, force majeure, or comprehensive general liability insurance, as may be applicable | Section 84, PPP Code IRR
10 | Acceptance tests and procedures | Section 84, PPP Code IRR
11 | Warranty period and procedures (after transfer) and warranty security | Section 84, PPP Code IRR
12 | Lock-in conditions, as applicable | Section 84, PPP Code IRR
13 | Grounds for contract termination, including events of default, and effects of contract termination, including formula for Termination Payment, and manner and timeline of payment | Section 84, PPP Code IRR
14 | Conditions and procedures for lender step-in rights | Section 84, PPP Code IRR
15 | Conditions for acceptable permitted security interest | Section 84, PPP Code IRR
16 | The manner and procedures for the resolution of corruption | Section 84, PPP Code IRR
17 | Wind-up and transfer measures pursuant to Section 22 of the Code | Section 84, PPP Code IRR
18 | Compliance with all other applicable laws, rules, and regulation | Section 84, PPP Code IRR
19 | Total cost of the project, project specifications, and features | Section 84, PPP Code IRR
20 | Gender, social, disability, and environment safeguards | Section 84, PPP Code IRR
21 | Provisions on the use of dispute avoidance and Alternative Dispute Resolution (ADR) mechanisms pursuant to RA No. 9285, or the “Alternative Dispute Resolution Act of 2004” The contracting parties shall be given complete freedom to choose which ADR mechanisms to be followed, subject to applicable laws, rules, and regulations. | Section 84, PPP Code IRR
22 | Ownership or retention of patents, technology, and consultant reports | Section 84, PPP Code IRR
23 | Monitoring, evaluation and reporting scheme/plan for all safeguard-related mandatory provisions of the PPP Contract | Section 84, PPP Code IRR
24 | Provision requiring the procurement of Independent Consultant by the Implementing Agency, including roles and responsibilities | Section 110, PPP Code IRR; and Section 30(a), PPP Code
25 | Applicable interest rates to be applied in PPP contracts | Section 138, PPP Code IRR
26 | Temporary or Permanent Takeover by the Government | Section 150, PPP Code IRR
27 | In case of a JV Company, dividends from the net profits proportionate to the equity contributions of the Implementing Agency and the Private Sector Partner | Section 103 c(v), PPP Code IRR; and Section 11(e), PPP Code
28 | In case of JV projects, equity contribution, including assets, properties, and rights, and other allowable government undertakings not exceeding 50% of the Project Cost for Contractual JV; or 50% of the outstanding capital stock if JV Company | Section 103 c(iii), PPP Code IRR; and Section 11 (b)(1) and (2), PPP Code
29 | In case of JV projects, veto rights of the government | Section 103 c(i), PPP Code IRR; and Section 11 (a), PPP Code

## Sheet16 (hidden)
| Project Cost | a. Construction Performance Security |  | b. Operation Performance Security |  | c. Warranty Security |  | d. Handback Security
| in PHP M | in PHP M | % of Project Cost | in PHP M | % of Project Cost | in PHP M | % of Project Cost | in PHP M | % of Project Cost
DRP | 4788.13 |  | 2% | 100 adjusted in each year to an amount equal to 10% of Gross Revenue accrued during the previous year. |  | 250 |  | (i) the Handback Rectification Amount comprising the aggregate of the cost necessary to deliver the Handback Rectification Works exceeds (ii) the amount of the Operation Performance Security
DRP | 4504.59 |  | 2% | 100 adjusted in each year to an amount equal to 10% of Gross Revenue accrued during the previous year. |  | 250 |  | (i) the Handback Rectification Amount comprising the aggregate of the cost necessary to deliver the Handback Rectification Works exceeds (ii) the amount of the Operation Performance Security
CGY | 12748.35 |  | 2% | 100 adjusted in each year to an amount equal to 10% of Gross Revenue accrued during the previous year. |  | 250 |  | (i) the Handback Rectification Amount comprising the aggregate of the cost necessary to deliver the Handback Rectification Works exceeds (ii) the amount of the Operation Performance Security